## Slide 1
DECISION ADVANTAGE
Sponsor a small test
before claiming
a new offer.
A narrow, non-clinical test of whether capacity insight is consistently translated into a governed operational decision.
Internal sponsorship proposal | 19 October 2026
THE ASK
Sponsor a 90-minute internal workshop.
Approve a 12-week assessment only if the workshop names one candidate engagement and finds a gap that current tools and process do not already close.
WHAT YOU ARE SPONSORING
A reusable decision-contract method for one specialist clinic-capacity decision — not software, not clinical decision support, and not a claim that existing tools are inadequate.
THE SPONSOR DECISION
Give the idea 90 minutes. Stop if it duplicates what already works.
Notes: Source: User-supplied prior proposal and slide text. Core content is a hypothesis to test; it is not client evidence.

## Slide 2
THE NARROW HYPOTHESIS
2 / 9
The only question worth testing
Do capacity insights reliably become a named, time-bound operational decision?
1
Capacity insight
A planning view or model indicates a threshold may be breached.
2
Operational decision
Someone must decide what happens, by when, and within which permitted actions.
3
Evidence or stop
The decision, rationale, feasibility constraint and outcome are available — or the contract adds nothing.
This does not assert that a digital twin or current workflow lacks governance. It tests adequacy for one selected decision in one client context.
FALSIFIABLE BY DESIGN
Stop if the current record already shows owner, deadline, rationale, constraint and outcome reliably — or if the root cause is unavailable capacity.
Notes: Source: EY Ireland article supplied by the user, paraphrased: digital twins are valuable when anchored in a specific decision and inform planning. Decision Advantage makes no claim about gaps in twins.

## Slide 3
A BOUNDED FIRST TEST
5 / 9
Start with one specialist clinic-capacity decision
Synthetic oHCM-type scenario for an internal workshop — no client or patient data.
SCENARIO
Demand is projected to exceed planned appointment capacity over six weeks.
A planning view forecasts utilisation above an agreed threshold and a possible delay to therapy start. The operational question is whether and how to activate a capacity response.
The test is the governance of the response — not clinical prioritisation, treatment choice or patient monitoring.
WHAT WOULD BE DECIDED?
Confirm an extra clinic session
Seek cross-cover capacity
Escalate an unavailable-resource constraint
Record that no feasible response exists
Boundary: all triggers, thresholds and actions are illustrative. Their clinical and operational appropriateness is for the client to define and verify.
Notes: Source: User-supplied scenario. All thresholds and responses are illustrative and are not clinical guidance.

## Slide 4
THE REUSABLE METHOD
6 / 9
A decision contract makes the test inspectable
If the client already has this evidence for the selected decision, the proposal should stop.
Contract field | Question to evidence
Trigger | Which threshold and evidence start the decision?
Owner + deadline | Who is accountable, who is deputy, and by when?
Permitted response | Which non-clinical capacity actions are allowed?
Escalation | When and to whom does an unresolved decision move?
Rationale | Why was the chosen response selected or declined?
Feasibility class | Decision delayed / action infeasible / outcome not achieved
Verified outcome | What happened after the response and who checked it?
WHY THIS MATTERS
It separates
"we saw a risk"
from
"we governed
a response."
A useful asset only if clients see the same missing record repeatedly.
NOT A NEW OPERATING SYSTEM
A structured diagnostic and assurance record for one existing operational decision.
Notes: Source: User-supplied Decision Advantage decision-contract work. The table is editable and designed as a workshop diagnostic.

## Slide 5
STEP 1
7 / 9
The 90-minute workshop is the decision gate
A low-risk internal test on a synthetic or published scenario. It must end with one candidate engagement, or a stop.
1
0–10
Set boundaries
Scope, non-clinical limits and stop conditions.
2
10–25
Walk the scenario
Identify the capacity insight and candidate decision.
3
25–40
Map today
Identify roles, tools, hand-offs and records.
4
40–60
Draft contract
Set owner, deadline, action, escalation and outcome.
5
60–75
Red-team it
Test duplication, capacity constraints and burden.
6
75–90
Make the call
Stop / assess / design recommendation.
THE WORKSHOP MUST DISPROVE SOMETHING
Current tools already close the gap; the issue is capacity, not governance; the additional record is burdensome; or there is no plausible client sponsor/buyer.
Notes: Source: User-supplied workshop plan. Duration and outputs are a proposed internal test, not an EY process claim.

## Slide 6
STEP 2 — ONLY IF STEP 1 PASSES
8 / 9
A 12-week assessment earns the right to become an offer
No software build or deployment is assumed. The output is evidence, not advocacy.
WEEKS 1–3
Diagnose
Map one workflow; review existing tools; write a falsifiable gap statement.
›
WEEKS 4–7
Design
Co-design the contract, assurance controls and measurement plan.
›
WEEKS 8–10
Shadow mode
Observe a non-clinical test route with agreed client governance.
›
WEEKS 11–12
Decide
Produce an evidence pack and recommend stop, iterate or package.
GO ONLY IF ALL FOUR ARE TRUE
✓
A plausible client decision exists
✓
Existing tools do not already close it
✓
A non-clinical test route is feasible
✓
The method is reusable beyond one engagement
Before Week 1: named sponsor · client route · resource approval · IP and independence clearance
Notes: Source: User-supplied assessment plan. Any client governance, information governance or commercial conditions are verify before a client assessment.

## Slide 7
SPONSOR DECISION
9 / 9
Sponsor the test — not the conclusion
The value of Step 1 is a disciplined answer about whether to stop.
STEP 1: SPONSOR NOW
A 90-minute internal workshop
Endorse the test and convene Life Sciences, AI & Data / twin, health operations and risk colleagues [names to confirm]. About two hours of preparation; synthetic or published scenario. Step 1 must end with one candidate engagement, or a stop.
STEP 2: SPONSOR ONLY IF PASSED
A 12-week client-linked assessment
Access to a suitable engagement or team, a named EY lead and light-touch oversight: [__] partner hours and [__] team members over 12 weeks. Only with a named sponsor, a client route, resource approval and IP and independence clearance.
WHAT YOU GET BACK
A clear stop / assess / design recommendation, a draft reusable method, and evidence on whether there is a differentiated client conversation worth pursuing.
Verify before external use: EY sponsorship process, suitable engagement/client access, and ownership and permitted use of the prototype and any IPCI-related material.
Notes: Source: User-supplied request. Verify EY structure, priorities, sponsorship process, IP ownership/confidentiality and client governance requirements before use.