DECISION ADVANTAGE

Partner sponsorship proposal

Test whether a specialist clinic-capacity decision needs a lightweight, auditable decision contract after capacity insight is available.

| THE DECISION REQUEST Sponsor a 90-minute internal workshop. Authorise a 12-week assessment only if the workshop shows a real, client-relevant gap that existing process and tools do not already close. | WHAT IS BEING TESTED A narrow operational hypothesis: can a defined capacity alert be turned into a named, time-bound, non-clinical decision with a recorded rationale, feasibility constraint and verified outcome? |
| --- | --- |

The proposition, in plain language

Capacity insight can identify a potential problem. The test is whether the subsequent operational decision is consistently owned, made on time, explainable and followed through. Decision Advantage does not claim that a digital twin, dashboard or existing workflow lacks these controls. It tests whether they are adequate for one selected decision in one client context.

| This is | This is not |
| --- | --- |
| A reusable advisory method to map and test one operational decision contract. | A hospital platform, clinical decision support, a replacement for a digital twin, or a claim that current tools are inadequate. |

Candidate first use case: specialist clinic capacity

Synthetic workshop scenario: a specialist cardiac clinic expects demand for a new therapy to exceed planned appointment capacity over six weeks. A planning model indicates utilisation above a chosen threshold and a possible delay to therapy start. The workshop asks how the capacity response is governed; it does not address patient selection, treatment or monitoring.

| Decision-contract field | Illustrative workshop content |
| --- | --- |
| Trigger | Forecast utilisation crosses an agreed threshold, supported by the existing planning view. |
| Accountable owner | Named operational capacity owner, with a deputy. |
| Time-bound response | Acknowledge and decide within an agreed operational window. |
| Permitted actions | Confirm extra clinic session; seek cross-cover; escalate an unavailable-resource constraint; or record no feasible action. |
| Rationale and outcome | Record why the action was selected, whether it was feasible, and whether the expected operational result occurred. |

What would make the idea unnecessary

The current process and tools already provide a reliable record of the owner, deadline, decision, rationale, feasibility constraint and outcome for the selected decision.

The delay is primarily a structural lack of staff, rooms or funding rather than a decision-governance problem.

Adding a contract creates material workflow burden or does not have a plausible client owner and buyer.

Step 1 — the sponsored 90-minute internal workshop

| Timing | Activity | Decision output |
| --- | --- | --- |
| 0–10 min | Set scope, non-clinical boundaries and explicit stop conditions. | Shared definition of the test. |
| 10–25 min | Walk through the synthetic specialist clinic scenario. | Candidate decision and trigger. |
| 25–40 min | Map how the decision is presumed to work today. | Existing tools, roles and records. |
| 40–60 min | Complete the decision-contract template. | Draft owner, deadline, actions, escalation and outcome. |
| 60–75 min | Red-team duplication, capacity constraints and workflow burden. | Disproof evidence and risks. |
| 75–90 min | Score client relevance and repeatability. | Stop / assess / design recommendation. |

Step 2 — only if Step 1 passes: 12-week assessment

Purpose: establish whether a real client workflow has a decision-governance gap and whether a reusable advisory asset can address it. This is a scoped assessment, not a software build or deployment.

| Phase | Weeks | Output |
| --- | --- | --- |
| Diagnose | 1–3 | Workflow map, existing-tool review and a falsifiable gap statement. |
| Design | 4–7 | Co-designed decision contract, assurance controls and measurement plan. |
| Shadow mode | 8–10 | Non-clinical observation using an agreed test route; no autonomous action. |
| Decision | 11–12 | Evidence pack, repeatability assessment and stop / go recommendation. |

Sponsor commitment and return

| The sponsor provides | The sponsor receives |
| --- | --- |
| Step 1: endorsement; 90 minutes from relevant colleagues; approximately two hours of preparation; permission to use a synthetic or published scenario. Step 2 only if approved: access to a suitable engagement or team, a named EY lead and light-touch oversight. | A clear answer on whether there is a client-relevant, differentiated advisory test; a draft reusable method and template; a decision on whether to stop, assess further or design a repeatable offer. |

Decision criteria

| Proceed to assessment only if | Stop if |
| --- | --- |
| A plausible client decision exists; the gap is not already closed by current process/tools; a non-clinical test route is feasible; and the method looks reusable beyond one engagement. | The proposed contract duplicates adequate controls; unavailable capacity is the real cause; participants judge the extra record as burdensome; or no sponsor/client buyer can be identified. |

Questions to verify before any external use

Verify: EY Ireland practice structure, sponsorship process, client access route and resource commitments.

Verify: ownership, confidentiality and permitted external use of the independently developed prototype and any IPCI-related material.

Verify: client governance, information-governance and procurement requirements for any later assessment or shadow-mode work.

Verify: whether the selected client already has a tool or operating model that meets the decision-contract criteria.

Appendix note — IPCI: the concept may be referenced internally as background only. Ownership and permitted use must be verified before any external use.