DECISION ADVANTAGE

Partner sponsorship proposal

Test whether a specialist clinic-capacity decision needs a lightweight, auditable decision contract after capacity insight is available.

| THE DECISION REQUEST Sponsor a 90-minute internal workshop. Authorise a 12-week assessment only if the workshop names one candidate engagement and shows a real, client-relevant gap that existing process and tools do not already close. | WHAT IS BEING TESTED A narrow operational hypothesis: can a defined capacity alert be turned into a named, time-bound, non-clinical decision with a recorded rationale, feasibility constraint and verified outcome? |
| --- | --- |

The proposition, in plain language

Capacity insight can identify a potential problem. The test is whether the subsequent operational decision is consistently owned, made on time, explainable and followed through. Decision Advantage does not claim that a digital twin, dashboard or existing workflow lacks these controls. It tests whether they are adequate for one selected decision in one client context.

| This is | This is not |
| --- | --- |
| A reusable advisory method to map and test one operational decision contract. | A hospital platform, clinical decision support, a replacement for a digital twin, or a claim that current tools are inadequate. |

Fit with EY’s digital twin work

EY Ireland’s published article on digital twins of patient journeys describes models that are anchored in a specific decision, test changes before implementation and combine data with clinical and operational expertise. Decision Advantage is complementary only where a twin engagement needs a consistent record of the operational decision that follows a model’s insight: who owned it, by when, why, and what happened. It does not claim that twins lack decision governance. One hypothesis to test is whether recorded decisions and outcomes can be compared with the twin’s assumptions. Any claim about wider EY priorities beyond the article: verify.

How the idea got here

| Stage | What it showed | Not yet validated |
| --- | --- | --- |
| Thought leadership | A hypothesis about delayed or unowned decisions in hospital operations | That the problem exists at a real site |
| Build Week prototype | The decision lifecycle works on synthetic data | Performance, adoption, client value |
| HIHI submission and feedback | Crowded market; differentiation and a real gap not yet evidenced | A differentiated, evidenced gap |
| Narrowing | One decision contract; lead case moved from ED boarding to a specialist clinic-capacity decision to match EY’s published twin work | Client demand |
| Today | This proposal and a 90-minute workshop request | A client workflow, buyer, data route or commercial case |

The move from ED boarding to specialist clinic capacity improves alignment with EY’s published work. It does not validate demand. The prototype has been tested on synthetic data only.

Candidate first use case: specialist clinic capacity

Synthetic workshop scenario: a specialist cardiac clinic expects demand for a new therapy to exceed planned appointment capacity over six weeks. A planning model indicates utilisation above a chosen threshold and a possible delay to therapy start. The workshop asks how the capacity response is governed; it does not address patient selection, treatment or monitoring.

| Decision-contract field | Illustrative workshop content |
| --- | --- |
| Trigger | Forecast utilisation crosses an agreed threshold, supported by the existing planning view. |
| Accountable owner | Named operational capacity owner, with a deputy. |
| Time-bound response | Acknowledge and decide within an agreed operational window. |
| Permitted actions | Confirm extra clinic session; seek cross-cover; escalate an unavailable-resource constraint; or record no feasible action. |
| Rationale and outcome | Record why the action was selected, whether it was feasible, and whether the expected operational result occurred. |

What would make the idea unnecessary

The current process and tools already provide a reliable record of the owner, deadline, decision, rationale, feasibility constraint and outcome for the selected decision.

The delay is primarily a structural lack of staff, rooms or funding rather than a decision-governance problem.

Adding a contract creates material workflow burden or does not have a plausible client owner and buyer.

Step 1 — the sponsored 90-minute internal workshop

| Timing | Activity | Decision output |
| --- | --- | --- |
| 0–10 min | Set scope, non-clinical boundaries and explicit stop conditions. | Shared definition of the test. |
| 10–25 min | Walk through the synthetic specialist clinic scenario. | Candidate decision and trigger. |
| 25–40 min | Map how the decision is presumed to work today. | Existing tools, roles and records. |
| 40–60 min | Complete the decision-contract template. | Draft owner, deadline, actions, escalation and outcome. |
| 60–75 min | Red-team duplication, capacity constraints and workflow burden. | Disproof evidence and risks. |
| 75–90 min | Score client relevance and repeatability. | Stop / assess / design; one candidate engagement, or a stop. |

Step 2 — only if Step 1 passes: 12-week assessment

Purpose: establish whether a real client workflow has a decision-governance gap and whether a reusable advisory asset can address it. This is a scoped assessment, not a software build or deployment. Gates before Week 1: a named sponsor, a client route, resource approval, and IP and independence clearance.

| Phase | Weeks | Output |
| --- | --- | --- |
| Diagnose | 1–3 | Workflow map, existing-tool review and a falsifiable gap statement. |
| Design | 4–7 | Co-designed decision contract, assurance controls and measurement plan. |
| Shadow mode | 8–10 | Non-clinical observation using an agreed test route; no autonomous action. |
| Decision | 11–12 | Evidence pack, repeatability assessment and stop / go recommendation. |

Sponsor commitment and return

| The sponsor provides | The sponsor receives |
| --- | --- |
| Step 1: endorsement; 90 minutes from Life Sciences, AI & Data / twin, health operations and risk colleagues [names to confirm]; approximately two hours of preparation; permission to use a synthetic or published scenario. Step 2 only if approved: access to a suitable engagement or team, a named EY lead and light-touch oversight ([__] partner hours and [__] team members over 12 weeks), after a named sponsor, a client route, resource approval and IP and independence clearance. | A clear answer on whether there is a client-relevant, differentiated advisory test, with one named candidate engagement or a stop; a draft reusable method and template; a decision on whether to stop, assess further or design a repeatable offer. |

Decision criteria

| Proceed to assessment only if | Stop if |
| --- | --- |
| A candidate engagement and a plausible client decision exist; the gap is not already closed by current process/tools; a non-clinical test route is feasible; and the method looks reusable beyond one engagement. | The proposed contract duplicates adequate controls; unavailable capacity is the real cause; participants judge the extra record as burdensome; no candidate engagement exists, or no sponsor/client buyer can be identified. |

Questions to verify before any external use

Verify: EY Ireland practice structure, sponsorship process, client access route and resource commitments.

Verify: ownership, confidentiality and permitted external use of the prototype and any IPCI-related material.

Verify: client governance, information-governance and procurement requirements for any later assessment or shadow-mode work.

Verify: whether the selected client already has a tool or operating model that meets the decision-contract criteria.

Appendix note — IPCI: the concept may be referenced internally as background only. Ownership and permitted use must be verified before any external use.